## semantics_kpis
Sr No | KPI Name | Description | Formula | Mapped Tables / Columns
1 | Swap FTR | Tracks first time right success rate of swap execution | Only 1 entry vs Total Swaps | tmo_retro_mbt_tracker(site_code, market, area, region), pm_tracker(site_id, swap_actual_date, call_test), tmo_hse_supervision(site_id, ndpd_project_id)
2 | NDPd Cycle Time – CPO received to Cx Start | Indicates the number of sites where Microwave (MW) link installation is complete | ms_1550_construction_start_actual – CPO received date | ms_1550_construction_start_actual
3 | Pending MW Link Acceptance | MW installation completed but link not formally accepted | Count of sites where MW installation complete (pj_a_4425_mw_installation_complete_finish) populated AND MW Link Final Accepted not populated | tmo_retro_mbt_tracker(pj_project_id, pj_a_4425_mw_installation_complete_finish, pj_a_5300_mw_link_final_accepted_and_operational_finish), pm_tracker(project_id)
4 | Pre-Con Validated | Pre-con validated count | Count of "MS 1313 Pre-Construction Package Validated - Actual" | ms_1313_pre_construction_package_validated_actual
5 | Site Walk CPO Rate | Total number of Drone Site Walk CPOs available against POR sites | Availability rate of Drone CPO based on Project ID in MBT & NDPd | Rider column for C0213 to be added in OSDP table
6 | SCOP Submitted | SCOP submitted volumetric count | NDPd – Count of "MS 1557 Review Tower Quality Media Checklist Reviewed and Submitted" | ms_1557_ndpd_punch_checklist_reviewed_and_submitted
7 | Integration Start Delay After Construction | Construction completed but Integration did not start on same day | Count of sites where construction complete (pj_a_5175_construction_complete_finish) populated and integration start delayed | tmo_retro_mbt_tracker(pj_project_id, pj_a_5175_construction_complete_finish, pj_a_5270_integration_start_finish), pm_tracker(project_id)
8 | Scoping Package Submitted | Scoping package submitted volumetric count | NDPd: Count of "MS 1331 Scoping and Quoting Package Submitted" | ms_1331_scoping_package_submitted_actual
9 | NDPd Cycle Time – Site Walk to Scoping | Cycle time between Site Walk completion and Scoping validation | ms_1327_scoping_and_quoting_package_validated_actual – max(ms_1316_pre_con_site_walk_completed_actual, ms_1321_talon_view_drone_svcs_actual) | ms_1327_scoping_and_quoting_package_validated_actual, ms_1316_pre_con_site_walk_completed_actual, ms_1321_talon_view_drone_svcs_actual
10 | Quote Approval | Quote approval volumetric count | Count of "MS 1333 Scoping and Quoting Package Submitted Actual" | ms_1333_scoping_package_approved_by_customer_actual
11 | Prerequisite Pending for Construction Start – GSD PM | Sites pending with GSD PM based on prerequisite readiness | SMP/SPO | MBT: Projectid, NDPd: 1555 CPO, NDPd: 1555 SPO, MBT: Hard Cost Vendor = Nokia, NDPd: SMP ID
12 | TMO Rejected the SCOP Submitted | TMO rejected SCOP submitted volumetric count | Count of "TW Media Checklist Rejected by TMO" | punchlist_received_from_t_mobile
13 | Total POR Sites Count | Daily POR site count | Daily count | MBT-Dump (ssiteid, createdate), NDPd-Dump (customersitecode, createdate)
14 | One Quote Submission | One quote completion count | Cumulative count of "MS 1331 Scoping and Quoting Package Submitted" | ms_1331_scoping_package_submitted_actual
15 | Prerequisite Pending from GC | List of prerequisites dependent on GC | Site Access / Crane Requirement confirmation | PM Tracker: Site Access Status, PM Tracker: Crane Availability Status, MBT: Projectid
16 | Count of Stop Work Notification Sent | Track number of sites non-compliant after L4 escalation | No. of sites not resolved after L4 escalation vs non-compliance sites | Daily HSE Action Report
17 | Construction NTP Acceptance Rate | Measures percentage of projects where Construction NTP accepted by GC | Count of sites where pj_a_4100_construction_ntp_accepted_by_gc_finish populated | tmo_retro_mbt_tracker(pj_project_id, pj_a_4100_construction_ntp_accepted_by_gc_finish), pm_tracker(project_id)
18 | Construction Notice to Proceed (NTP) Status | Tracks NTP status at project level | Based on NTP acceptance population | pjprojectstatus, ssiteid, n.packagename
19 | SPO Created for Sites without CPO | Sites without SPO for the CPOs | — | pjprojectstatus, ssiteid, n.packagename, n.ms1321talonsporequesteddate, n.ms1555spoissuedp2ovendorname
20 | Prerequisite Pending on Customer | List of prerequisites that are dependent on customer | NTP Pending (4100) / Material / CHG ID | MBT: PJ:Project ID; MBT: PJ(A EC Pending (3710)); MBT: PJ(A 4075) Construction NTP Submitted to GC-Finish; MBT: PJ:RFDS Purpose (RFDS); NDPD: 1555 CPO; PJ(A 3875) BOM Received (BOM in AIMS)-Finish; MBT: SM:Service Management ID
21 | Building Permit Approval Cycle Time | Measures the average number of days from application for a building permit to final approval | Average days between RAN Building Permit Applied (pj_a_3650_ran_building_permit_applied_finish) and RAN Building Permit Approved (pj_a_3675_ran_building_permit_approved_finish) | tmo_retro_mbt_tracker(pj_project_id, pj_a_3650_ran_building_permit_applied_finish, pj_a_3675_ran_building_permit_approved_finish), pm_tracker(project_id)
22 | L2 Compliance Count | Number of sites compliant after L2 escalation | No. of sites compliant after L2 escalation vs non-compliant sites | Daily HSE Action Report
23 | L3 Compliance Count | Number of sites compliant after L3 escalation | No. of sites compliant after L3 escalation vs non-compliant sites | Daily HSE Action Report
24 | NDPd Cycle Time – Civil Cx Start to Civil Cx Complete | NDPd Cycle Time – Civil Cx Start to Civil Cx Complete | ms_1551_civil_construction_complete – ms_1549_civil_construction_start_actual | ms_1551_civil_construction_complete, ms_1549_civil_construction_start_actual
25 | Integration Cycle Time | Measures the average number of days required to complete the integration process | Average days between Integration Start (pj_a_5270_integration_start_finish) and Integration Complete (pj_a_5275_integration_complete_finish) | tmo_retro_mbt_tracker(pj_project_id, pj_a_5270_integration_start_finish, pj_a_5275_integration_complete_finish), pm_tracker(project_id)
26 | Material Availability Pending with Customer | BOM ordered but material availability pending at customer warehouse | 3850 A non-blanks vs 3875 A blanks | MBT: PJ:Project ID; MBT: PJ(A 3850) BOM Submitted (BOM in BAT)-Finish; MBT: PJ(A 3900) All BAT Orders Received-Finish; MBT: PJ(A 3875) BOM Received (BOM in AIMS)-Finish
27 | Integration Completion Delay | Integration started but not completed on the same day (SLA breach) | Count of sites where Integration Start (pj_a_5270_integration_start_finish) is populated and Integration Complete delayed | tmo_retro_mbt_tracker(pj_project_id, pj_a_5270_integration_start_finish, pj_a_5275_integration_complete_finish)
28 | SCOP Resubmitted Approval | SCOP Resubmitted approval volumetric count | NDPd / SCOP tracker: Count of “TW Punch List Re-Submitted to TMO” | punch_checklist_reviewed_and_resubmitted_to_t_mobile, ssiteid, pjprojectid, ssservicemanagementid
29 | Service Management ID | Service Management ID (CHG ID) availability to generate NAS outage request | Need to get sites with or without service ID | MBT: Projectid; NDPD: 1555 CPO; NDPD: 1555 SPO; MBT: Hard Cost Vendor = Nokia; NDPD: SMP ID
30 | CPO Available but SPO Creation Pending | Sites with CPO available but SPO creation not done | CPO available but SPO is blank for SMP ID created sites | MBT: Projectid; NDPD: 1555 CPO; NDPD: 1555 SPO; MBT: Hard Cost Vendor = Nokia; NDPD: SMP ID
31 | Zoning Approval Cycle Time | Tracks the average duration (days) from zoning application submission to approval | Average days between RAN Zoning Applied (pj_a_3550_ran_zoning_applied_finish) and RAN Zoning Approved (pj_a_3575_ran_zoning_approved_finish) | tmo_retro_mbt_tracker(pj_project_id, pj_a_3550_ran_zoning_applied_finish, pj_a_3575_ran_zoning_approved_finish), pm_tracker(project_id)
32 | Enhanced Services CPO Rate | Total number of Enhanced CPOs available against Base CPOs for POR sites | Need to calculate CPO availability rate based on Project ID in MBT & sites in NDPd for which CPO is available | Rider column for MB4/MB4B/C0222 to be added in OSDP table
33 | % of Sites Meets Cx Complete SLA – NSD (MB) | Cx Start to Cx Complete Cycle Time – MB for TMO Vendor Scorecard | If [por_category] = “New Build” then (pj_a_5175_construction_complete_finish – pj_a_4225_construction_start_finish); Track: If Today – ms_1557_punch_checklist_reviewed_and_submitted_to_tmobile_at < 30 then “On Track”; if 31–60 then “Off Track”; >60 then “Intervention” | MBT data table; ms_1557_punch_checklist_reviewed_and_submitted_to_tmobile_at
34 | NDPd Ageing – COP Submission to COP Approved | NDPd ageing from COP submission to COP approval | Today – ms_1557_punch_checklist_reviewed_and_submitted_to_tmobile_at; <30 = “On Track”; 31–60 = “Off Track”; >60 = “Intervention” | MBT-Dump: pjprojectid, ssiteid, packagename, pjprojectstatus; NDPd-Dump: tmobileprojectid, basesporerequesteddate
35 | CPO Availability Rate | Total number of base CPOs available against POR sites | Need to calculate availability rate of CPO based on Project ID in MBT & sites in NDPd for which CPO is available | pjprojectstatus, ssiteid, n.packagename
36 | SPO with CPO | No. of sites for which SPO is available for the available CPOs | — | pjprojectstatus
37 | COP Received to COP Approved Cycle Time – MB | COP received to COP approved cycle time – MB for TMO Vendor Scorecard | If (pj_a_5525_approve_close_out_binder_finish − pj_a_5500_receive_close_out_binder_finish) > 30 → “Out of SLA”, else “In SLA” | MBT data table, pj_a_5525_approve_close_out_binder_finish, pj_a_5500_receive_close_out_binder_finish
38 | Prerequisite Pending from GSD PM | List of prerequisites that are dependent on GSD PM | SMP Creation / SPO Creation | MBT: Project ID; NDPD: 1555 CPO; NDPD: SMP ID; NDPD: 1555 SPO
39 | Punchlist Submission – TW | Punchlist submission to Customer (14 Days) | TW Punch List Re-Submitted to TMO – TW Checklist Rejected by TMO-DEC-RSA | rgn_region, pj_project_type, pj_a_4225_construction_start_finish
40 | Site Completion Cycle Time | Measures the average number of days from project start (Cx Start) to On-Air for Site Mods and New Builds | Average (Completion Objective Actual Date − PJ(A 4225) Construction Start Finish) | pm_tracker(project_id), pj_a_1550_mount_analysis_received_finish, ms1555_construction_complete_actual_date
41 | Work Time Estimate (WTE) | WTE (Work Time Estimate) Equipment Installation | Installation Cycle time (Days) * 7.5 * 60 | pj_a_1550_mount_analysis_recieived_finish
42 | AAV vs MW | Comparing sites AAV vs MW | count(pj_backhaul_task_selection = 'AAV') / total count | mbt
43 | Integration to On-Air Delay | Sites integrated but not On-Air within 3 days | Count of sites where (On-Air Date − Integration Complete Date) > 3 days | tmo_retro_mbt_tracker(pj_project_id, pj_a_5275_integration_complete_finish, pj_completion_objective_actual_date)
44 | GC Compliance Ratio | Track total number of compliant sites | % of compliant sites vs total validated sites GC wise | Daily HSE Action Report
45 | NDPd Ageing – Cx Complete to COP Submission | NDPd ageing from Cx Complete to COP submission | If Today − ms_1555_construction_complete_actual < 15 → “On Track”; 15–30 → “Off Track”; >30 → “Intervention Required” | ms_1555_construction_complete_actual
46 | On-Air Pending after Construction Done | Sites where construction is complete but On-Air is still pending | Count of sites where Construction Complete (pj_a_5175_construction_complete_finish) populated and On-Air pending | tmo_retro_mbt_tracker(pj_project_id, pj_a_5175_construction_complete_finish, pj_completion_objective_actual_date)
47 | Entitlement Completion Rate | Tracks the percentage of projects where all necessary entitlements (e.g., zoning) are complete | Count of sites where All Entitlement Complete (pj_a_3725_all_entitlement_complete_finish) is populated | tmo_retro_mbt_tracker(pj_project_id, pj_a_3725_all_entitlement_complete_finish), pm_tracker(project_id)
48 | RFDS Scoping to Approval Cycle Time | Measures the average number of days required to complete RFDS scoping | Average days between RAN Project Scoping Finish (pj_a_1000_ran_project_scoping_finish) and RFDS Scoping Approved Date (rfds_scoping_approved_date_rfds) | tmo_retro_mbt_tracker(pj_project_id, pj_a_1000_ran_project_scoping_finish, rfds_scoping_approved_date_rfds), pm_tracker(project_id)
49 | MW Installation Lead Time | Lead time from MW Cx start to complete | pj_a_4425_mw_installation_complete_finish − MW Cx Start | mbt
50 | Sites Feasible for BOM Creation | Sites which are ready for BOM | PJ: RFDS Purpose (RFDS) is Ready for BOM AND RFDS Ready for BOM Approved Date is populated | MBT: PJ:RFDS Purpose (RFDS); MBT: PJ:RFDS Ready for BOM Approved Date (RFDS); MBT: PJ:RFDS Status (RFDS)
51 | Pre NTP Validation | Validate and finalize configuration based on Pre-NTP document (2 days SLA) | Pre-NTP Received Date (1310) − Pre-NTP Validation Date (1313) | ms_1313_pre_construction_package_validated_actual; ms_1315_pre_construction_package_rejected_actual
52 | NDPd Cycle Time – E2E | NDPd Cycle Time – E2E from Site Walk to COP acceptance | ms_1559_cop_approved_by_t_mobile_actual − max(ms_1316_pre_con_site_walk_completed_actual, ms_1321_talon_view_drone_svcs_actual) | ms_1559_cop_approved_by_t_mobile_actual; ms_1316_pre_con_site_walk_completed_actual; ms_1321_talon_view_drone_svcs_actual
53 | Civil Start Delay (>60 Days) | Number of sites where civil construction has not started within 60 days after entitlement completion | Count of sites where (Civil Start Date (pj_a_4250_civil_construction_start_finish) − Entitlement Completion Date (pj_a_3710_ran_entitlement_complete_finish)) > 60 | rgn_region, pj_project_type, pj_a_3710_ran_entitlement_complete_finish, pj_a_4250_civil_construction_start_finish, pm_tracker(project_id)
54 | Sites with Approval for NTP | Construction NTP approved | Construction NTP approved | MBT: siteid; MBT: projectid; MBT: projectstatus; MBT: pj_a_4075_construction_ntp_submitted_to_gc_finish; MBT: PJ(A 4100) Construction NTP Accepted by GC-Finish
55 | Pending Building Permit Approval | Indicates number of sites where building permit applied but not approved | Count of sites where RAN Building Permit Applied (pj_a_3650_ran_building_permit_applied_finish) is populated and approval not populated | tmo_retro_mbt_tracker(pj_project_id, pj_a_3650_ran_building_permit_applied_finish, pj_a_3675_ran_building_permit_approved_finish), pm_tracker(project_id)
56 | Civil Completion Delay | Number of sites where civil work started but not completed within SLA (21 days) | Count of sites where (Civil Completion Date (pj_a_4750_civil_construction_complete_finish) − Civil Start Date (pj_a_4250_civil_construction_start_finish)) > 21 | rgn_region, pj_project_type, pj_a_4250_civil_construction_start_finish, pj_a_4750_civil_construction_complete_finish, pm_tracker(project_id)
57 | Total No. of Sites vs Available Crews | Total number of sites vs available crews | Crews then “On Track” else “Add Crews Required”; Remove sites with Cx Complete Delay codes (pj_construction_complete_delay_code). Exclude blanks | pj_construction_complete_delay_code
58 | HSE Check-in % | Number of sites HSE compliant | NDPD HSE | NDPC form answers: siteid, sessionid, sessionstatus, h.hse_sessions_count; tmo_retro_mbt_tracker(site_code, market, area, region)
59 | Call Test Pass Rate | Measures percentage of sites that pass call test after swap | Passed call tests / Total tested sites | pm_tracker(site_id, swap_actual_date, call_test)
60 | Power Installation Cycle Time | Measures average number of days from ordering permanent power services to installation | Average days between Permanent Power Ordered (pj_a_4450_permanent_power_ordered_finish) and Permanent Power Installed (pj_a_4550_permanent_power_installed_finish) | tmo_retro_mbt_tracker(pj_project_id, pj_a_4450_permanent_power_ordered_finish, pj_a_4550_permanent_power_installed_finish), pm_tracker(project_id)
61 | LL/Construction NTP Available | LL/Construction NTP available site list | LL/Construction NTP in MB | MBT: siteid; MBT: projectid; MBT: projectstatus; MBT: pj_a_4075_construction_ntp_submitted_to_gc_finish; MBT: TOrd (A4000) LL NTP Received-Finish
62 | 48 Hrs Monitoring Completed | 48 hours monitoring completed volumetric | Count of PJ(A 5275) Integration Complete-Finish vs Nokia PM RTT | ms_1970_integration_complete_actual; ms_1557_ndpd_punch_checklist_reviewed_and_submitted
63 | ZD % | Zero Defect Installation Quality | (No. of sites SCOP submitted without internal punchpoints during Cx / Total SCOP submitted sites) × 100 | gdc_quality_audit_date
64 | Pending RFDS Approval | Indicates number of sites where RFDS scoping completed but final approval pending | Count of sites where RAN Project Scoping Finish (pj_a_1000_ran_project_scoping_finish) populated and RFDS approval not populated | tmo_retro_mbt_tracker(pj_project_id, pj_a_1000_ran_project_scoping_finish, rfds_scoping_approved_date_rfds), pm_tracker(project_id)
65 | Forecast vs Actual – Entitlement | Customer forecasted sites vs actual for entitlement | (Number of PJ: Completion Objective Actual Date / Total Sites) × 100 | rgn_region, pj_project_type, pj_completion_objective_actual_date; pm_tracker(project_id)
66 | On-Air Completion Rate (%) | Percentage of sites that reached On-Air compared to total planned sites | (Number of PJ: Completion Objective Actual Date / Total Sites) × 100 | pm_tracker(project_id)
67 | L4 Compliance Count | Number of sites compliant after L4 escalation | No. of sites compliant after L4 escalation vs non-compliant sites | Daily HSE Action Report
68 | Close Out Binder Approval Rate | Tracks percentage of projects where final close-out binder documentation approved | Count of sites where Approve Close Out Binder (pj_a_5525_approve_close_out_binder_finish) populated | tmo_retro_mbt_tracker(pj_project_id, pj_a_5525_approve_close_out_binder_finish), pm_tracker(project_id), mbt
69 | MW to IX Start Lead Time | Lead time from MW installation to IX start | pj_a_5270_integration_start_finish − MW installation complete date | mbt
70 | Construction Drawing Approval Cycle Time | Measures the average number of days for construction drawings to be reviewed and approved | Average days between Construction Drawings Ordered (pj_a_2200_construction_drawings_ordered_finish) and Construction Drawings Approved (pj_a_2275_final_construction_drawings_approved_finish) | tmo_retro_mbt_tracker(pj_project_id, pj_a_2200_construction_drawings_ordered_finish, pj_a_2275_final_construction_drawings_approved_finish), pm_tracker(project_id)
71 | NTP Approved | NTP approved volumetric count | NDPd: Count of “MS 1406 Tower NTP Received - Actual” | ms_1406_tower_ntp_received_actual
72 | RIOT Green Lead Time | Small Cell – Time required to turn RIOT Green | MS5200 – e911 request submission date | E2E tracker table (to be integrated with OSDP)
73 | H&S FTR% | Track number of first-time compliant sites | No. of compliant sites vs total validated sites | Daily HSE Action Report
74 | SCOP Approval Pending | SCOP approval pending from TMO | Blank | ms_1559_cop_approved_by_t_mobile_actual
75 | AAV Construction Cycle Time | Tracks average duration (days) from start of AAV (Access & Availability) | Average days between AAV Construction Start (pj_a_4945_aav_construction_start_finish) and AAV Construction Complete (pj_a_4950_aav_construction_complete_finish) | tmo_retro_mbt_tracker(pj_project_id, pj_a_4945_aav_construction_start_finish, pj_a_4950_aav_construction_complete_finish), pm_tracker(project_id)
76 | Customer Pendency Blocks | List actions pending against customer for starting scheduling | EC Pending (3710) / CPO not available (EEPT) / POR not assigned (MB) | MBT: Project ID; MBT: PJ(A EC Pending (3710)); NDPD: 1555 CPO
77 | Cx Completed | Cx completed count | Count of “MS 1555 Tower Works Complete - Actual” | ms_1555_construction_complete_actual
78 | Integration Completed | Integration completed volumetric count | NDPd: Count of “MS 1899 All Planned Technologies Integrated - Actual” | ms_1899_all_planned_technologies_integrated_actual
79 | L1 Compliance Count | No. of sites compliant after crew contact | No. of sites compliant after crew lead contact vs non-compliant | Daily HSE Action Report
80 | NDPd Cycle Time – Cx Start to Cx Complete | NDPd cycle time from Cx Start to Cx Complete | ms_1550_construction_start_actual to ms_1555_construction_complete_actual | ms_1555_construction_complete_actual, ms_1550_construction_start_actual
81 | NDPd Cycle Time – Quote Submitted to CPO Received | NDPd cycle time from quote submission to CPO received | CPO received date − ms_1333_scoping_package_approved_by_customer_actual | CPO received date, ms_1333_scoping_package_approved_by_customer_actual
82 | POR Sites Year Wise Count | Year-wise budgeted POR sites | — | —
83 | % e911 Requested | How many nodes have been requested till now | e911 requests / nodes entitled % | E2E tracker (to be integrated with OSDP)
84 | NDPd Cycle Time – Scoping to Quoting | NDPd cycle time from scoping to quoting | ms_1331_scoping_package_submitted_actual − ms_1327_scoping_and_quoting_package_validated_actual | ms_1331_scoping_package_submitted_actual, ms_1327_scoping_and_quoting_package_validated_actual
85 | % of Sites Meets Cx Complete SLA – Site Mod (MB) | Cx Start to Cx Complete Cycle Time – MB for TMO Vendor Scorecard | If (pj_a_5175_construction_complete_finish − pj_a_4225_construction_start_finish) > expected_down_time → “Out of SLA” else “In SLA” | MBT data table; pj_a_5175_construction_complete_finish; pj_a_4225_construction_start_finish
86 | NDPd Cycle Time – COP Submission to COP Approved | NDPd cycle time from COP submission to COP approval | ms_1559_cop_approved_by_t_mobile_actual − ms_1557_punch_checklist_reviewed_and_submitted_to_tmobile_at | ms_1559_cop_approved_by_t_mobile_actual; ms_1557_punch_checklist_reviewed_and_submitted_to_tmobile_at
87 | Pending Construction Drawings Approval | Construction drawings submitted/received but final approval pending | pj_a_2225_construction_drawings_received_finish populated AND pj_a_2275_final_construction_drawings_approved_finish blank | tmo_retro_mbt_tracker(pj_project_id, pj_a_2225_construction_drawings_received_finish, pj_a_2275_final_construction_drawings_approved_finish), pm_tracker(project_id)
88 | SCOP Review by Customer – TW | SCOP acceptance by customer (14 Days SLA) | TW Checklist Submitted to Customer – TW Checklist Accepted by Customer | TMO-DEC-RSA
89 | COP Rejection Rate | Number of rejected checkpoints / total checkpoints | If (Rejected Checkpoints / Total Checkpoints) <1% → 10; <2% → 8; <2.5% → 6; <4% → 4; else 0 | (Total rejected checkpoints / Total checkpoints) logic
90 | Civil NTP Acceptance Cycle Time | Time from Civil NTP issued to GC until GC acceptance | Average days between Civil NTP Submitted to GC (pj_a_4025_civil_ntp_submitted_to_gc_finish) and Civil NTP Accepted by GC (pj_a_4050_civil_ntp_accepted_by_gc_finish) | tmo_retro_mbt_tracker(pj_project_id, pj_a_4025_civil_ntp_submitted_to_gc_finish, pj_a_4050_civil_ntp_accepted_by_gc_finish), pm_tracker(project_id)
91 | Network Acceptance Rate | Sites accepted by operations | (Accepted Sites pj_a_5275_integration_complete_finish / On-Air Sites pj_completion_objective_actual_date) × 100 | pj_a_5275_integration_complete_finish; pj_completion_objective_actual_date
92 | Site Survey Completed | Site survey completed volumetric count | NDPd Volume: Count of MS 1316 Pre Con Site Walk Completed | ms_1316_pre_con_site_walk_completed_actual
93 | Pending Permanent Power Installation | Sites where permanent power ordered but installation pending | Permanent Power Ordered (pj_a_4450_permanent_power_ordered_finish) populated AND pj_a_4550_permanent_power_installed_finish blank | tmo_retro_mbt_tracker(pj_project_id, pj_a_4450_permanent_power_ordered_finish, pj_a_4550_permanent_power_installed_finish), pm_tracker(project_id)
94 | SCOP FTR % | First Time Right outcome of TMO review | (SCOP Accepted Sites / Total SCOP Submitted Sites) × 100 | ms_1559_cop_approved_by_t_mobile_actual; customer_quality_audit_date
95 | Prerequisite Pending for Construction Start – Customer | Sites that are pending with customer based on prerequisite readiness | NTP / Material / CHG ID / Outage Approval | MBT: Projectid; MBT: PJ(A 3710) RAN Entitlement Complete-Finish; MBT: PJ(A 4075) Construction NTP Submitted to GC-Finish; MBT: SM: Service Management ID; NAS: New table with column for outage details
96 | Scoping Completed | Scoping completed volumetric count | NDPd: Count of “MS 1327 Scoping and Quoting Package” | ms_1327_scoping_and_quoting_package_validated_actual
97 | NDPd Ageing – Cx Start to Cx Complete | NDPd ageing from Cx Start to Cx Complete | If (Today − ms_1550_construction_start_actual) < 25 → “Intervention Required”; >25 → “Off Track”; Exclude sites where ms_1555_construction_complete_actual is populated | ms_1550_construction_start_actual; ms_1555_construction_complete_actual
98 | Tower Top Equipment Installation Rate | Tracks percentage of sites where tower top equipment installation is completed | Count of sites where Install Tower Top Equipment (pj_a_5100_install_tower_top_equipment_finish) is populated | tmo_retro_mbt_tracker(pj_project_id, pj_a_5100_install_tower_top_equipment_finish), pm_tracker(project_id)
99 | Feasible for Submitting BOM | Sites ready for BOM submission | RFDS Purpose = Ready for BOM AND RFDS Ready for BOM Approved Date populated AND Cx date ≤ 35 days AND BOM allocation request in MBT = 1 | MBT: PJ:RFDS Purpose (RFDS); MBT: PJ:RFDS Ready for BOM Approved Date (RFDS); MBT: PJ:RFDS Status (RFDS); MBT: PJ(A 4225) Construction Start-Finish; MBT: PJ: BOM Allocation Request
100 | Prerequisite Pending from GSD DEC | List of prerequisites dependent on GSD DEC | Talon SCOP session | MBT: Projectid; NDPC: SCOP Session Link